Community Health Action Plan 2016

County: Haywood                                                                          Period Covered:  2015-2018

Partnership/Health Steering Committee, if applicable:  Healthy Haywood

Community Health Priority identified in the most recent CHA: Mental health

###### Local Community Objective:  (Working description/name of community objective) Reduce the rate of mental health-related visits to emergency departments (per 10,000).

###### (check one):  X New          Ongoing (addressed in previous Action Plan)

- Baseline Data: (State measure/numerical value.  Include date and source of current information):  (waiting to receive from local partners)

- For continuing objective provide the updated information: (State measure/numerical value.  Include date and source of current information):  N/A

- Healthy NC 2020 Objective that most closely aligns with focus area chosen below:  Reduce the rate of mental health-related visits to emergency departments (per 10,000).

Population(s)

- Describe the local target population that will be impacted by this community objective: The 2015 Community Health Assessment provided several numbers regarding the mental health of Haywood County.  Though 96% of adults reported not being limited by a mental health concern, another figure gave a different picture.  Sixteen percent reported having more than seven poor mental health days in the past month.  Nearly one fourth of individuals do not typically receive needed social or emotional support.  Over 7% did not get the mental health care or counseling that they needed in the past year.  Over 6% reported being dissatisfied with life.  For those questions asked during the previous health assessment, no improvement was noted.

- Total number of persons in the target population specific to this action plan: 2,873 (individuals affected by a mental health problem)

- Total number of persons in the target population to be reached by this action plan:  280 (number attending evidence-based interventions)

- Calculate the impact of this action plan:

(Total # in B divided by total # in A) X 100% =9.7% of the target population reached by the action plan.)

Healthy North Carolina 2020 Focus Area Addressed:  Each of the two CHA priorities selected for submission must have a corresponding Healthy NC 2020 focus area that aligns with your local community objectives.

- Check below the applicable Healthy NC 2020 focus area(s) for this action plan.

For more detailed information and explanation of each focus area, please visit the following websites: http://publichealth.nc.gov/hnc2020/foesummary.htm     AND       http://publichealth.nc.gov/hnc2020/

| Tobacco Use Physical Activity & Nutrition Injury Sexually Transmitted Diseases/Unintended Pregnancy | Maternal & Infant Health Substance Abuse Mental Health Infectious Disease/Foodborne Illness Oral Health | Social Determinants of Health Environmental Health Chronic Disease Cross-cutting |
| --- | --- | --- |

Selection of Strategy/Intervention Table

- Complete this table for all strategies/interventions that you plan to implement.

- At least two of the three selected community health priorities must be from the 13 Healthy North Carolina 2020 (HNC 2020) focus areas.  For these 2 priorities, there must be 2 evidence based strategies (EBS) for each action plan.  (Insert rows as needed if you choose more than 2 EBS.)

| Strategy/Intervention(s) | Strategy/Intervention Goal(s) | Implementation Venue(s) | Resources Utilized/Needed for Implementation |
| --- | --- | --- | --- |
| Name of Intervention: Mental Health First Aid/Youth Mental Health First Aid http://www.mentalhealthfirstaid.org/cs/about/research/ Community Strengths/Assets: Haywood Regional Medical Center (behavioral health unit), Balsam Center, Meridian Behavioral Health Services, Appalachian Community Services of WNC, Mobile Crisis, Smoky Mountain Center MCO | S.M.A.R.T Goals: A minimum of four classes will be held by May 2018 with 25 people attending per class. | Target Population(s): Stakeholders and clients Venue: A community building | Resources Needed: Manual for participants, food, action plan will be developed, publicity, staff time, space, evaluation forms. |
| Name of Intervention: Providing Question/Persuade/Refer (QPR) training to community members and form suicide prevention plan https://www.qprinstitute.com/research-theory Community Strengths/Assets: Haywood Regional Medical Center (behavioral health unit), Balsam Center, Meridian Behavioral Health Services, Appalachian Community Services of WNC, Mobile Crisis, Smoky Mountain Center MCO | S.M.A.R.T Goals: Hold a minimum of six QPR trainings with community members and organizations. | Target Population(s): Stakeholders and clients Venue: A community building | Resources Needed: Manual for participants, food, publicity, staff time, space, evaluation forms. |

Interventions Specifically Addressing Chosen Health Priority (Insert rows as needed.)

| - INTERVENTIONS: - SETTING, & TIMEFRAME | LEVEL OF INTERVENTION CHANGE | COMMUNITY PARTNERS’ Roles and Responsibilities | PLAN HOW YOU WILL EVALUATE EFFECTIVENESS |
| --- | --- | --- | --- |
| Intervention: Mental Health First Aid/Youth Mental Health First Aid New Ongoing Completed Setting: Community building Target population: Stakeholders and community members New Target Population: Y N Start Date – End Date (mm/yy): 11/16-05/18 Targets health disparities: Y N | Individual/Interpersonal Behavior Organizational/Policy Environmental Change | Lead Agency: Smoky Mountain MCO Role: Training New partner Established partner Target population representative: Kate Glance Role: Training facilitator New partner Established partner Partners: Haywood County Health and Human Services Agency, Haywood Community College, Haywood County Public Library Role: Promotion, food provision (HCHHSA), allowing use of space. New partner Established partner How you market the intervention: Social media, e-mail, newspaper, verbal announcements | Expected outcomes: Four trainings will be held and 100 people will receive training. Anticipated barriers: Any potential barriers? Y N If yes, explain how intervention will be adapted: List anticipated intervention team members: Megan Hauser, Kate Glance, SMC, Anita Wilkins Do intervention team members need additional training? Y N If yes, list training plan: Quantify what you will do: Four trainings will be held and 100 people will receive training. List how agency will monitor intervention activities and feedback from participants/stakeholders: Post-training evaluations will be given to participants. Data trends for suicide rates, mental health emergency department visits and poor mental health days will be followed. Evaluation: Please provide plan for evaluating intervention: Post-training evaluations will be given to participants. Data trends for suicide rates, mental health emergency department visits and poor mental health days will be followed. |

Interventions Specifically Addressing Chosen Health Priority (Insert rows as needed.)

| - INTERVENTIONS: - SETTING, & TIMEFRAME | LEVEL OF INTERVENTION CHANGE | COMMUNITY PARTNERS’ Roles and Responsibilities | PLAN HOW YOU WILL EVALUATE EFFECTIVENESS |
| --- | --- | --- | --- |
| Intervention: Question, Persuade Refer training and development of suicide prevention plan New Ongoing Completed Setting: Human services or other community building Target population: Stakeholders and clients New Target Population: Y N Start Date – End Date (mm/yy): 2/17-5/18 Targets health disparities: Y N | Individual/Interpersonal Behavior Organizational/Policy Environmental Change | Lead Agency: Smoky Mountain MCO Role: Training New partner Established partner Target population representative: Kate Glance Role: New partner Established partner Partners: Haywood County Health and Human Services Agency, Haywood Community College, Haywood County Public Library Role: Promotion, food provision (HCHHSA), allowing use of space. New partner Established partner How you market the intervention: Social media, e-mail, newspaper, verbal announcements | Expected outcomes: A minimum of six trainings will be held with 30 participants per training. Anticipated barriers: Any potential barriers? Y N If yes, explain how intervention will be adapted: List anticipated intervention team members: Kate Glance, Megan Hauser, Anita Wilkins Do intervention team members need additional training? Y N If yes, list training plan: The facilitator, Kate Glance, will be trained in October 2016. Quantify what you will do: A minimum of six trainings will be held with 30 participants per training. List how agency will monitor intervention activities and feedback from participants/stakeholders: Post-training evaluations will be given to participants. Data trends for suicide rates, mental health emergency department visits and poor mental health days will be followed. Evaluation: Please provide plan for evaluating intervention: Post-training evaluations will be given to participants. Data trends for suicide rates, mental health emergency department visits and poor mental health days will be followed. |